## Workback
Team members ¦ Membres de l'équipe R = Responsible ¦ Responsable A = Accountable ¦ Approbateur C = Consulted ¦ Consulté I = Informed ¦ Informé
Deliverable ¦ Livrable | Tasks ¦ Tâches | Wendy | John | Michael | Start Date ¦ Date de début | Deadline ¦ Date limite | Status ¦ Statut | Notes
Communications Plan | Develop draft strategic communications plan | C | C | R |  |  | Complete ¦ Complète
Comms Plan | Finalize communications plans | C | C | R |  |  | In Progress ¦ En cours
Visual Identity | Create logo drafts / ideas |  |  | R |  |  | Not Started ¦ Pas encore commencé
Visual Identity | Review logo drafts and narrow concept |  |  | R |  |  | Complete ¦ Complète
Visual Identity | Finalize logo | C | C | R |  |  | In Progress ¦ En cours
Visual Identity | Confirm colour palette |  |  | R |  |  | Not Started ¦ Pas encore commencé
Visual Identity | Confirm brand typography | I | I | R |  |  | Complete ¦ Complète
Visual Identity | Create image bank | C | C | R |  |  | In Progress ¦ En cours
Visual Identity | Create template social graphics | C | C | R |  |  | Not Started ¦ Pas encore commencé
Visual Identity | Create brand guide | C | C | R |  |  | Complete ¦ Complète
Visual Identity | Finalize brand | I | I | R |  |  | In Progress ¦ En cours
Visual Identity | Translate brand guide | A | A | C |  |  | Not Started ¦ Pas encore commencé
Lexicon | Develop lexicon | I | I | R |  |  | Complete ¦ Complète
Lexicon | Lexicon review | C | C | R |  |  | In Progress ¦ En cours
Lexicon | Finalize lexicon | C | C | R |  |  | Not Started ¦ Pas encore commencé
Lexicon | Lexicon term translations |  |  | R |  |  | Complete ¦ Complète
Key Messaging | Draft key messages | C | C | R |  |  | In Progress ¦ En cours
Key Messaging | Finalize key messages | C | C | C |  |  | Not Started ¦ Pas encore commencé
Key Messaging | Translate key messages | I | I | R |  |  | Complete ¦ Complète
Website Development | Create site map | C | C | R |  |  | Complete ¦ Complète
Website Development | Confirm platform |  |  | R |  |  | In Progress ¦ En cours
Website Development | Build draft page layouts (including pictures) | C | C | R |  |  | Not Started ¦ Pas encore commencé
Website Development | Finalize page layouts | I | I | R |  |  | Complete ¦ Complète
Website Development | Draft copy | C | C | R |  |  | In Progress ¦ En cours
Website Development | Finalize web copy | C | C | R |  |  | Not Started ¦ Pas encore commencé
Website Development | Translate web copy | I | I | R |  |  | Complete ¦ Complète
Website Development | Verify domain and security | I | I | R |  |  | In Progress ¦ En cours
Website Development | QA Website | I | I | R |  |  | Not Started ¦ Pas encore commencé
Website Development | Launch | I | I | R |  |  | Complete ¦ Complète
Announcement Event | Create event scenario | I | I | R |  |  | In Progress ¦ En cours
Announcement Event | Create event registation | I | I | R |  |  | Not Started ¦ Pas encore commencé
Announcement Event | Promote event | I | I | R |  |  | Complete ¦ Complète
Announcement Event | Develop speaking notes | C | C | C |  |  | In Progress ¦ En cours
Announcement Event | Create slidedeck | [5 empty] | Not Started ¦ Pas encore commencé
Announcement Event | Translations | [5 empty] | Complete ¦ Complète
Announcement Event | Announcement takes place | [5 empty] | In Progress ¦ En cours
News Release | Create draft news release | I | I | R |  |  | Not Started ¦ Pas encore commencé
News Release | Finalize news release | [5 empty] | Complete ¦ Complète
News Release | Translate news release | I | I | R |  |  | Complete ¦ Complète
News Release | Set up on website | C | C | R |  |  | In Progress ¦ En cours
News Release | Publish | I | I | R |  |  | Not Started ¦ Pas encore commencé
News Release | Conduct media outreach and pitching |  |  | R |  |  | Complete ¦ Complète
News Release | Media outreach follow up | R | R | R |  |  | In Progress ¦ En cours

## Sheet11 (hidden)
Deliverable | Action Items | Start Date | Deadlines | Notes
EOI's | confirming CF's participation on CSRF | September | Oct 14th | Deadline date communicated to CF's
| Finalize list of CF's participation (list of 37 CF's not particpating) | 2022-10-14 | Nov 8th
| Cross reference CF's membership dues are up to date/good standing |  | NOv 10th
Mapping | Confirming CF's boundaries & overlapping | Oct 17th | Oct 28th
| Final map edits here | Oct 17th | Nov 10th | All final map edits to Emily (GIS)
Honoraria & Allocation | Template email via zoho sent to CF's re: honoraria, allocation, key messages and a link to set up meeting with PC for any Q's | week of Nov 7th?
Lexicon | Develop CSRF lexicon | 2022-10-31 | 2022-11-03
Lexicon | Lexicon review | 2022-11-04 | 2022-11-10
Lexicon | Finalize lexicon | 2022-11-11 | 2022-11-15
Lexicon | Lexicon term translations | 2022-11-15 | 2022-11-18
National Ad-Buy | Begin national ad-buy process | 2022-10-21 | 2022-11-22
National Ad-Buy | National ad-buy socials | 2022-11-23
National Ad-Buy | Continued weekly check ins | 2022-11-23
Key Messaging | Draft key messages | 2022-10-31 | 2022-11-04
Key Messaging | Finalize key messages | 2022-11-08 | 2022-11-10
Key Messaging | Translate key messages | 2022-11-14 | 2022-11-17
Joint Landing Page | First draft of site map | 2022-09-26
Joint Landing Page | Confirm eligibility quiz platform | 2022-10-06 | 2022-10-14
Joint Landing Page | Build page + layout | 2022-09-26 | 2022-10-13
Joint Landing Page | Intermediary layout review | 2022-10-13 | 2022-10-20
Joint Landing Page | Nov 22/23 - Announcement
Joint Landing Page | Finalize ENG copy for website | 2022-11-10 | 2022-11-15
Joint Landing Page | Translate web copy | 2022-11-16 | 2022-11-18
Joint Landing Page | QA Soft Launch Page | 2022-11-21 | 2022-11-22
Joint Landing Page | Launch Page | 2022-11-23 | 2022-11-23
Joint Landing Page | Jan 6 - Portal Open
Joint Landing Page | Add final resources & portal links | 2022-10-14 | 2022-11-04
Joint Landing Page | update eligibility quiz | 2022-11-10 | 2022-11-14
Application Form | Team Awesome Working Session | 2022-11-07
Application Form | Internal review of application form | 2022-11-08 | 2022-11-11 | 1-day hold next week to finalize all 3 documents (assessment, form, guide) to share with team leads - let's clarify who specifically on each team is involved in this review
Application Form | Incoporation of internal reviews | 2022-11-14 | 2022-11-16 | Suggest 1-day hold to finalize all 3 documents (assessment, form, guide) to share with strategic partners
Application Form | Strategic partner reviews | 2022-11-16 | 2022-11-23 | Session for review of feedback as a group (to decide what is/isnt possible to change)
Application Form | Incoporation of final reviews | 2022-11-23 | 2022-12-02 | 6 working days to ensure all reviews are final - formal review process?
Application Form | Translation of application form | 2022-12-02 | 2022-12-12
Application Form | Consistency revisions | 2022-12-12 | 2022-12-16 | Consistency: brand, language, & translations
Application Form | Buiding EN application form in SMA | 2022-12-02 | 2022-12-06
Application Form | EN SMA QA testing | 2022-12-06 | 2022-12-16
Application Form | Buiding FR application form in SMA | 2022-12-19 | 2022-12-21
Application Form | FR SMA QA testing | 2022-12-21 | 2022-12-23
Application Form | Branding PDF application form | 2023-01-02 | 2022-01-04 | Add note in PDF - if applying to CRC or UW or CFC XYZ - how many PDF forms?
Application Form | Creating PDF permalink | 2023-01-02 | 2022-01-04
Application Form | Application form final QA & finalize | 2023-01-02 | 2022-01-04 | Launch ready
Application Form | Uploading guidelines to landing page | 2023-01-06
Assessment Criteria | Team Awesome Working Session | 2022-11-07 |  | 1-day hold next week to finalize all 3 documents (assessment, form, guide) to share with team leads
Assessment Criteria | Internal review of Assessment Criteria | 2022-11-08 | 2022-11-11
| Incoporation of internal reviews | 2022-11-14 | 2022-11-16 | Suggest 1-day hold to finalize all 3 documents (assessment, form, guide) to share with strategic partners
Assessment Criteria | Strategic partner reviews | 2022-11-16 | 2022-11-23
Assessment Criteria | Incoporation of final reviews | 2022-11-23 | 2022-12-02
Assessment Criteria | Translation of criteria | 2022-12-02 | 2022-12-12
Assessment Criteria | Consistency revisions | 2022-12-12 | 2022-12-16 | Consistency: brand, language, & translations
Assessment Criteria | Buiding assessment form in SMA | 2022-12-12 | 2022-12-16
Assessment Criteria | Branding PDF criteria doc | 2023-01-02 | 2022-01-04
Assessment Criteria | Creating PDF permalink | 2023-01-02 | 2022-01-04
Assessment Criteria | Assessmennt criteria finalized | 2022-01-04 |  | Launch ready
Assessment Criteria | Uploading guidelines to landing page | 2023-01-06 |  | Will this be a publicly avail doc
Program Guidelines | Team Awesome Working Session | 2022-11-07 |  | 1-day hold next week to finalize all 3 documents (assessment, form, guide) to share with team leads
Program Guidelines | Internal review of Program Guidelines | 2022-11-08 | 2022-11-11
Program Guidelines | Incoporation of internal reviews | 2022-11-14 | 2022-11-16 | Suggest 1-day hold to finalize all 3 documents (assessment, form, guide) to share with strategic partners
Program Guidelines | Strategic partner reviews | 2022-11-16 | 2022-11-23
Program Guidelines | Incoporation of final reviews | 2022-11-23 | 2022-12-02
Program Guidelines | Translation of program gudielines | 2022-12-02 | 2022-12-12
Program Guidelines | Consistency revisions | 2022-12-12 | 2022-12-16 | Consistency: brand, language, & translations
Program Guidelines | Branding program gudielines | 2023-01-02 | 2022-01-04
Program Guidelines | Creating PDF permalink | 2023-01-02 | 2022-01-04
Program Guidelines | Uploading guidelines to landing page | 2023-01-06
NF announcement (Nov 21) | Create event scenario | 2022-10-24 | 2022-11-03
NF announcement (Nov 21) | Develop speaking notes | 2022-11-07
NF announcement (Nov 21) | Create slidedeck | 2022-11-07
NF announcement (Nov 21) | Create news release & media advisory | 2022-11-14 | 2022-11-16
NF announcement (Nov 21) | Translations | 2022-11-16 | 2022-11-22
NF announcement (Nov 21) | Announcement takes place | 2022-11-22
Amplification Package | Begin developing amplification package | 2022-11-07
Amplification Package | Complete first draft | 2022-11-07
Amplification Package | Review period | 2022-11-09
Amplification Package | Finalize amplifcation package | 2022-11-09 | 2022-11-16
Amplification Package | Translation of amplifcation package | 2022-11-16 | 2022-11-18
Amplification Package | Share amplifcation package with networks | 2022-11-21 | 2022-11-21
Portal Open (Jan 6) | Create event scenario | 2022-11-07 | 2022-11-17
Portal Open (Jan 6) | Develop speaking notes | 2022-11-07 | 2022-11-17
Portal Open (Jan 6) | Create slidedeck | 2022-11-14 | 2022-11-17
Portal Open (Jan 6) | Create news release & media advisory | 2022-10-24 | 2022-11-03
Portal Open (Jan 6) | Translations | 2022-11-17 | 2022-11-22
Portal Open (Jan 6) | Announcement takes place | 2023-01-06
🎉 LAUNCH |  |  | 2023-01-06
Social Promotion | Amplify program on socials | 2022-11-07 | Continued throughout program
Screencap Videos | Screencast for applicants (How to apply via SMA) | 2022-11-16
1-pager Program Guidelines | Create applicant guide 1-pager | 2022-11-23 | 2022-11-28
1-pager Program Guidelines | Review of EN 1-pager | 2022-11-28 | 2022-11-28
1-pager Program Guidelines | Translations | 2022-11-30 | 2022-12-12
1-pager Program Guidelines | Branding | 2022-12-12 | 2022-12-16
1-pager Program Guidelines | Create permalinks | 2022-12-16 | 2023-01-13
1-pager Program Guidelines | Share | 2023-01-13 | 2023-01-13
Applicant Learning Sessions | Create event scenario |  |  | Need to select dates for learning sessions & divide responsibilities b/t NFs - comms teams to connect
Applicant Learning Sessions | Develop speaking notes
Applicant Learning Sessions | Create slidedeck
Applicant Learning Sessions | Translations
Applicant Learning Sessions | Session takes place
Inbound Emails | FAQs - Applicants | November | Continued
🛑 APPLICATION DEADLINE |  | 2023-02-21